# PROJECT: IMPLEMENTATION OF THE STRATEGIC ACTION PROGRAM TO ENSURE THE INTEGRATED AND SUSTAINABLE MANAGEMENT OF TRANSBOUNDARY WATER RESOURCES IN THE AMAZON RIVER BASIN CONSIDERING CLIMATE VARIABILITY AND CHANGE

TERMS OF REFERENCE

FOR THE HIRING OF A CONSULTANT SPECIALIZED IN FUNDRAISING AND PROJECT DEVELOPMENT TO ENSURE THE IMPLEMENTATION OF THE OTCA'S STRATEGIC ACTION PROGRAM

Funding Agency: Global Environment Facility (GEF)

Implementing Agency: UN Environment Program

Executing Agency: Amazon Cooperation Treaty Organization (ACTO).

Project duration: 4 years

Brasilia, 2026

TERMS OF REFERENCE

FOR THE HIRING OF A CONSULTANT SPECIALIZED IN FUNDRAISING AND PROJECT DEVELOPMENT TO ENSURE THE IMPLEMENTATION OF THE OTCA'S STRATEGIC ACTION PROGRAM

- BACKGROUND

Within the framework of the Amazon Cooperation Treaty, the Amazon Cooperation Treaty Organization (ACTO) and its Permanent Secretariat (PS/ACTO) have been established in Brasilia, with international legal status, with the purpose of improving and institutionally strengthening the process of cooperation, coordination and joint actions of its Member Countries to promote the sustainable development of the Amazon.

The main roles and functions of the PS/ACTO are to facilitate the exchange, knowledge, cooperation and joint projection among the Member Countries to fulfill the mandates of the Amazon Cooperation Treaty, generating consensus among the Member Countries to enable the implementation of activities, programs and projects, establishing spaces for political and technical dialogue among the Member Countries, among other actions.

In this context and within the framework of its regional action on water resources, ACTO has been executing the Amazon Basin Project - Implementation of the Strategic Action Program to Ensure the Integrated and Sustainable Management of Transboundary Water Resources in the Amazon River Basin Considering Climate Variability and Change, which is financed by the Global Environment Facility (GEF), with the United Nations Environment Program (UNEP) as implementing agency and the PS/ACTO as executing agency.

The main objective of this project is to advance in the implementation of the Strategic Action Program (SAP), promoting Integrated Water Resources Management (IWRM). The regional initiative is driven by previous agreements of the Amazonian countries that resulted in a shared vision and a common strategy for IWRM contained in the Strategic Action Program (SAP). In this context, the project supports countries to strengthen national capacity and regional governance for IWRM, improve adaptation to climate change, and ensure robust regional data to improve decision making and coordination on Amazon water resources, from the sources in the Andes to the river delta in the Atlantic, for a healthier Amazon ecosystem.

The Project is implemented under four components: i) Innovative governance model for Integrated Water Resources Management-IWRM in the Amazon Basin (from community to cabinet); ii) Building community resilience and protection of aquatic ecosystems to address the effects of climate variability and change in the Amazon Basin; iii) Integrated environmental monitoring and reporting based on indicators in response to indicators from relevant international conventions and agreements; and iv) Integrated model for monitoring, evaluating and communicating progress in the overall implementation of the Amazon SAP.

Key results of the project include the following:

- Permanent Regional IWRM Coordination Mechanism for the Amazon Basin, established in ACTO;

- National Water Authorities established in Guyana and Suriname;

- 15 national interventions and 2 bi/tri-national actions implemented in the basin reducing the vulnerability of the population and the impacts on ecosystems in the face of extreme hydro-climatic events and sea level rise;

- Training of 1,400 IWRM professionals and more than 10,000 local community members (at least 40% are women);

- Integrated environmental monitoring system covering an area of 600,000,000 ha;

The project is expected to reach more than 7.8 million people benefiting from project activities, corresponding to 20% of the Basin's population (ACTO & UN-MA, 2020).

Consequently, in order to achieve compliance with the SAP and establish institutional and financial sustainability for its implementation, it is planned to hire a Resource Mobilization specialist who, through annual articulation goals and funding commitments, will identify and consolidate a solid, diverse and loyal base of partners and donors to support the implementation of the SAP under a demand-driven approach, identifying strategic opportunities and deepening South-South Cooperation and Triangulation.

OTCA's current funding comes from three sources:

  - Annual dues from member countries. This contribution is earmarked for the administrative operation of the Permanent Secretariat.

  - South-South Cooperation (SSC), especially from Brazil's National Water Agency and the Brazilian Cooperation Agency, which supports the establishment of projects related to South-South cooperation and institutional strengthening between countries.

  - Multilateral Funds and Technical Assistance. ACTO has also received funding from BNDES, GEF, GIZ, ITTO, as well as from KfW, which are mainly aimed at improving transboundary capacities and governance, and Technical Assistance from the Inter- American Development Bank (IDB) and the World Bank.

The various sources of funding demonstrate the capacity and confidence that ACTO has with different donors and countries in the management of funds and the successful implementation of programs and projects related to the priorities given by the countries.

However, the organization's project portfolio is based solely on traditional sources of development financing.

The profile of ACTO's project portfolio is a reflection of the organization's long-term financing strategy (9RES / XIII MRE-OTCA / 01), which mostly allows funding from public sources, through national contributions from member countries (directly and as co-financing of projects) and bilateral/multilateral cooperation sources. Other sources of contribution considered by the resolution are state enterprises and joint ventures for specific topics related to the Strategic Agenda for Amazonian Cooperation (AECA), and state and private enterprises specifically in activities aimed at the appreciation and valuation of the Amazonian culture.

In this context, the main objective of the project's Financial Sustainability Strategy is to ensure that financial resources are available in a timely and sufficient manner for the implementation of the SAP and the achievement of IWRM in the Amazon Region. The objective is to improve the capacity of ACTO and its member countries to raise additional funds to ensure the achievement of SAP objectives in the short and medium term and local, national and transboundary IWRM in the long term. Furthermore, during the Project implementation period, ACTO will have the opportunity to become a space for discussion and exchange of information and financial experiences in water conservation, coordinator of the debate and development of future financing mechanisms for transboundary water conservation, such as water quality trading, carbon trading, as well as a reference for advice on the subject for member countries.

According to the Project Document, the Financial Sustainability Strategy is proposed as a three- pronged approach:

    - Improve ACTO's fundraising and financial planning capacity and ability to support the development of innovative financing mechanisms for water conservation in the basin;

    - Generate additional funds to support the implementation of the SAP, and;

    - Support member countries' capacity to design and implement incentive-based water financing mechanisms.

The Presidential Declaration of Belem and the Resolution of the Ministers of Foreign Affairs have prioritized a Financial Mechanism of ACTO, which allows the raising and capitalization of non- reimbursable financial resources from various sources, including voluntary contributions from Member Countries, international cooperation resources, development banks and other donors endorsed by the States Parties for the purpose of financing projects, programs, studies and other initiatives of national and regional scope, strengthening human and institutional capacities, as well as the permanent exchange of experiences among Amazonian countries. In this sense, this consultancy will contribute strategically to the discussion on the Financial Mechanism of ACTO, with a focus on ensuring the financial sustainability of the implementation of the SAP.

## ARTICULATION WITH OTHER STUDIES AND CONSULTANTS OF THE SAP AND PS/ACTO IMPLEMENTATION PROJECT

For the development of the consultancy there is a strict interrelation and feedback between the different products, activities and deliverables that are found in the implementation of the SAP. For this reason, the consultant must articulate the activities in order to achieve adequate planning and develop activities jointly with the Conservation Finance specialist.

To channel relevant national information, the Regional Project Coordination Unit will facilitate coordination with the National Project Coordination Units, which in turn will collaborate in managing the data and documented resources necessary to meet the goals of this consultancy.

The responsible consultant should establish a coordination mechanism to plan, develop and follow up on strategic activities with the Conservation Finance specialist and the SP/OTCA Environment and Climate Change Coordination.

## GENERAL OBJECTIVE

The consultant will be responsible for developing, delivering and implementing updated fundraising planning and securing financial resources necessary for the implementation and sustainability of the SAP.

## SPECIFIC OBJECTIVES

- Update and improve the SAP Resource Mobilization Strategy, develop its Action Plan.

- Implement the Action Plan by developing project profiles and mobilizing and raising funds.

- Promote the sustainability of mobilization and fundraising for the implementation of the SAP
.

## SPECIFIC OBJECTIVES, ACTIVITIES AND DELIVERABLES

Specific Objective 1. Update and improve the SAP Resource Mobilization Strategy, develop its Action Plan.

### Minimum activities required to meet specific objective 1.

- Review the SAP Resource Mobilization Strategy and develop an analysis matrix to link resource mobilization and funders to SAP strategic actions (including RADA, monitoring networks and Monitoring Protocols, etc.).

- Based on the work matrix, propose an update and improvement of the SAP's Resource Mobilization Strategy, linking potential funding sources/partners with the SAP's strategic actions. Based on the updated Resource Mobilization Strategy, develop an Action Plan incorporating the steps to be taken to generate advocacy and fundraising and mobilization.

- Assist PCU in the organization and development of the TWINNIG with Caribbean Biodiversity Fund CAR BlueEFin Project (activity likely to last beyond the planned period).

### Deliverables

- Working matrix and analysis of the relationship between the mobilization of resources and funders and the strategic actions of the SAP.

- Updated and detailed budget of the SAP's strategic actions.

- Updated SAP Resource Mobilization Strategy.

- SAP Resource Mobilization Strategy Action Plan

- TWINNIG progress reports.

Specific Objective 2. Implement the Action Plan through the development of project profiles and fundraising and mobilization.

### Minimum activities required to meet specific objective 2.

- Develop TORs for the hiring of a Conservation Finance Specialist.

- Prepare 4 Project concept notes (as per relevant funders' template) agreed with PS/ACTO/UCR, conduct/support follow-up in coordination with PS/ACTO and Conservation Finance specialist where applicable.

- Manage the implementation of the Action Plan for the mobilization and collection of funding for the implementation of the PAE, focusing on the project profiles developed.

- Participate and provide inputs and materials related to the SAP at the donor tables organized by the PS/ACTO.

### Deliverables of Specific Objective 2.

- TORs for the hiring of a Conservation Finance Specialist

- 4 Project concept notes (according to relevant funders' template)

- Reports of actions/progress of the Action Plan Implementation for the search of financing for the projects elaborated.

- Reports of the participation of 2 donor roundtables organized by the PS/ACTO including the inputs and materials produced.

Promote the sustainability of mobilization and fundraising for the implementation of the SAP.

### Minimum activities required to deliver deliverable 3

  - Consolidate alliances and promote networking with partners and funding agencies.

  - Develop a practical guide for mobilizing and raising funds for the implementation of the SAP/NAPs in the MPs available on the project website.

  - Prepare and organize a regional workshop for the exchange of experiences in IWRM financing within the scope of RADA.

.

### Deliverables of Specific Objective 3.

  - Activity reports and proposed agreements/letters of understanding with relevant partners and funding agencies.

  - Practical guide available on the Project's web page and presented in a Webinar to the MC/NPCU/RADA.

  - Report on the implementation of the Workshop for the exchange of experiences in financing IWRM in the RADA and a compendium of good practices.

## PRODUCTS

### Initial product. 20 days after signing the contract.

- Detailed Technical Proposal, adjusted, complemented and a Work Plan and methodological proposal presented schematically, to approach the consultancy.

- Terms of Reference to hire a Conservation Finance Specialist to support the development of activities focused on the activities of Product 1.3 of the project.

### First Product. 3 months after contract signature.

  - Work matrix and analysis of the relationship between the mobilization of resources and funders and the strategic actions of the SAP.

  - Updated and detailed budget of the SAP's strategic actions.

  - Updated SAP Resource Mobilization Strategy.

  - Action Plan for the SAP Resource Mobilization Strategy

  - TWINNIG progress reports.

### Second Product. 5 months after signing the contract.

  - 4 Project concept notes (according to relevant funder's model)

  - Reports of actions/progress of the Action Plan Implementation for the search of financing for the projects elaborated.

  - Progress reports on the participation of 2 donor roundtables organized by the PS/ACTO including inputs and materials produced (if the roundtables are not organized by the PS/ACTO the product may be delivered in the subsequent period).

### Third Product. At 7 months after the signing of the contract

- Activity reports and proposed technical cooperation agreements or MOUs with relevant partners and funding agencies on proposed projects.

- Practical guide for mobilizing and raising funds for the implementation of the SAP/NAPs in the MCs available on the project website and presented in a webinar to the MCs/NPCU/RADA.

- Workshop progress report and a compendium of best practices.

Fourth Product. Final reflective report and specific recommendations with actions for sustainability and continuity.

## PAYMENT SCHEDULE

| No. of products | % of payment | Deadline | Conditions |
| --- | --- | --- | --- |
| Work Plan TDRs | 20% | 20 days after contract signature | Approval of the initial report by the Regional Coordination and the SP/OTCA |
| Product 1 | 20% | 3 months after | Approval of the products by the |
|  |  | contract signature | Regional Coordination and the |
| Product 2 | 20% | 5 months after | SP/OTCA. |
|  |  | contract signature |  |
| Product 3 | 20% | 7 months after |  |
|  |  | contract signature |  |
| Product 4 | 20% | 13 months after |  |
|  |  | signing the contract |  |

CONSULTANT PROFILE AND TECHNICAL PROPOSAL

Academic Profile

  - Financial fundraising specialist with advanced university degree in economics, finance, MBA, public administration or related area.

  - Fluent in English and Spanish (spoken and written). Knowledge of other languages will be an asset: French, German and Portuguese.

  - IT: knowledge of specialized tools related to the position. Work Experience

  - Minimum experience of 7 years working in fundraising for international cooperation projects and/or development agencies or multilateral organizations. It will be necessary to demonstrate results of previous work, both in the achievement of objectives and in the quality of these.

  - Experience in the development of fundraising strategies by closing large volume transactions for project financing.

  - Experience in fundraising for environmental projects related to water resources and climate change.

  - Experience in campaign management and organization of private fundraising events.

  - Experience in the areas of Communication, Fundraising, Crowdfunding, Marketing.

  - Experience in fundraising for GEF projects is an advantage.

  - Demonstrated ability to work towards achieving ambitious goals and results.

  - Experience in multicultural environments will be an asset.

  - Negotiated or participated in the structuring of projects in alliance with different financing sources.

  - To have a network of contacts in multilateral organizations and other different public and private financing entities.

  - International Declaration of Ethical Principles of Fundraising and Crowdfunding.

### Technical Proposal

To apply, the applicant must submit a 5-page technical proposal explaining how to address each of the objectives, products and deliverables to be addressed.

## DURATION, REMUNERATION AND WORKING CONDITIONS

    - Consultancy contract for 14 months.

    - Remuneration upon delivery and approval of products.

## CLASSIFICATION CRITERIA

The classification will be made considering the following parameters:

| Professional Experience | 60 points |
| --- | --- |
| Technical proposal for application | 20 points |
| Interview | 20 points |

Qualification requirements (eliminatory):

| No. | Criterion (Yes/No) |
| --- | --- |
| 1. | Advanced university degree in economics, finance, MBA, public administration or related area. |
| 2. | Fluent in English and Spanish (spoken and written). Knowledge of other languages will be an asset: French, German and Portuguese. |
| 3. | Knowledge of specialized tools related to the position. |

## CONSULTANT'S TRAINING, QUALIFICATIONS AND EXPERIENCE

Professional experience (60 points)

| Specialization/Experience | Points |
| --- | --- |
| University degree (preferably Master's or PhD) in economics, finance, MBA, public administration or related area (Master's - 5 points, PhD - 10 points). | 10 |
| Minimum experience of 7 years working in fundraising for international cooperation projects and/or development agencies or multilateral organizations. It will be necessary to demonstrate results of previous work, both in the fulfillment of objectives and in the quality of these (7 years = 5 points, for each additional year 1 point up to 10 points). | 10 |
| Experience in the development of fundraising strategies by closing large volume transactions for project financing (2 points for each contract/year up to 10 points). | 10 |
| Experience in fundraising for environmental projects related to water resources and climate change (1 point for each contract up to 6 points). | 6 |
| Experience in campaign management and organization of private fundraising events (For each fundraising contract/event 1 point up to 7 points). | 7 |
| Experience in areas of Communication, Fundraising, Crowdfunding, Marketing (1 job - 3 points, 2 jobs - 5 points). Experience in fundraising for GEF projects is a plus (2 points). | 7 |
| Negotiated or participated in the structuring of projects in alliance with different financing sources (2 points for each project up to 6 points). | 6 |
| Network of contacts in multilateral organizations and other different public and private financing entities (2 points) | 2 |
| International Declaration of Ethical Principles of Fundraising and Crowdfunding. | 2 |
| TOTAL | 60 |

## DEPENDENCE AND SUPERVISION

The consultant will report to the Permanent Secretariat of the SP/OTCA and will be under the supervision of the Regional Coordinator of the Amazon Basin Project - PAE Implementation. The Regional Coordinator and the SP/OTCA will approve the consultant's products.

## DURATION

The contract will have a duration of 14 months.

## REMUNERATION

The budget (14 months) foreseen for the execution of this consultancy is USD 48,000 (Forty- eight thousand US Dollars). The amount of fees corresponds to the total amount to be paid for the consultancy, with no other amount pending to be paid.

## PLACE OF WORK

The Consultant Fundraising Specialist will provide the consultancy services from his/her place of residence and will coordinate his/her activities with the Project's RCU.

## ADDITIONAL INFORMATION

- Candidates must be available to start the consultancy work at the signing of the contract.

- Candidates must be willing and able to undertake international travel as required.

- The performance of the consultancy will not establish any relationship of dependency with the PS/ACTO.